## Methodology risk types
TYPE OF RISK | DESCRIPTION
Strategic | Relating to the rationale, quality and timely delivery of the project objective, final result or the project outputs (e.g. project results not achievable, major difficulties in delivering project outputs, problems with the inclusion of the key project target group)
Technology or innovativeness | Linked to the development, testing or implementation of innovative technology/product/process/solution; Intellectual Property Rights should also be thoroughly considered
Action plan | Related to the sequencing of individual activities and how this affects other parts of the work plan; the adequacy of the time required for each activity – realism of the delivery timetable; the parameters determining whether an activity can be implemented; underperformance of individual partners or partnership as a whole; qualitative and quantitative modifications to the project deliverables that might affect the main project outputs; modifications in the type and scope of activities, etc.
Investment plan | Linked to the investment delivery stages (feasibility study, permits and agreements including political approval and planning, procurement – including unsuccessful procurement, types of works to be undertaken), ownership or durability issues as well as Intellectual Property Rights, etc.
Procurement | Apart from the investment angle mentioned above – any other risk factors linked to the involvement of external experts or consultants in project implementation (e.g. externalized project management, etc.)
Communication | Potentially ineffective project communication strategy with internal or external effects (e.g. on target groups or stakeholders and hence the quality of outputs or deliverables), poor visibility on the NWE territory making roll-out difficult, non-compliance by partners or sub-contractors with Programme publicity rules, etc;
Finance | Linked to match-funding required for the project, accuracy of budgeting or financial milestone setting for ERDF subsidy contracts, State Aid or de minimis rule related, individual partner cash flows, etc.
Other | Any other type of risk that does not belong to the categories above.

## Risk rating quidelines
HOW TO DEFINE THE IMPACT AND LIKELIHOOD LEVELS? |  |  | HOW TO DEFINE THE RISK LEVEL? TO KNOW HOW TO PRIORITISE RISKS?
Impact
Rank | Impact | Likelihood
High | If a risk event occurs, a significant impact to the project result, output quality, schedule, budget or target group satisfaction will result. | Risk event is very likely to occur. | High | Medium | High | Critical
Medium | If a risk event occurs, a moderate impact to the result, output quality, schedule, budget or target group satisfaction will result. | Risk event is likely to occur. | Medium | Low | Medium | High
Low | If a risk event occurs, a minor impact to the result, output quality, schedule, budget or target group satisfaction will result. | Risk event is unlikely to occur or the probablility of it happening is low. | Low | Low | Low | Medium
|  |  |  | Low | Medium | High | Likelihood

## Risk log
Risk type (please choose one option from the drop-down menu) | Risk (please define the risk) | Explanation of the risk (please explain why the risk needs to be taken into consideration for the project to be successful) | Follow-up effects if the risk materialises (please identify the project elements that will be affected by the risk, to mitigate the risk effectively) | Impact (please choose one option from the drop-down menu) | Likelihood (please choose one option from the drop-down menu) | Risk level (please choose one option from the drop-down menu) | Planning (what to do) and implementation measures (how to do it)
[7 empty] | To prevent risk from happening | To reduce risk when it happens
Please remember to:
• Copy in the 3 main risks identified in the project Application Form
• Monitor these risks over the entire project duration as they are vital to your project success
The following risk types are recommended for use: |  | For the risk likelyhood and impact please use the green-light system for reference: | For the risk level please use the following references:
Action plan |  | Low | Low
Communication |  | Medium | Medium
Finance |  | High | High
Investment plan |  |  | Critical
Other
Procurement
Strategic
Technology and innovativeness