## Slide 1
La Guette Pilot and French (CNRS) Partners
Care-peat project – WP I2 – Investment
February 2019 – June 2021

## Slide 2
Validation of a hydrological and Sphagnum restoration and C-storage method in La Guette peatland by upscaling a previous small-scale experiment
La Guette peatland

## Slide 3
3: Frasne peatland
2: La Guette peatland
1: Landemarais peatland
4: Bernadouze peatland
Altitudinal gradient : 150 à 1500 m
La Guette peatland: central part of France, 25ha, 180m a.s.l. as part of the French Peatland Observatory
Owner: Neuvy/Barangeon city council / Manager: Community Villages & Forests
http://www.sno-tourbieres.cnrs.fr

## Slide 4
2 hydrological sub-systems
DOWN
UP
Hydrological restoration
Hydrological disturbance affected the plant cover…
• … but for the last 30 years, the site was invaded by Molinia and Betula spp caused by a road ditch which accelerates the peatland drainage
2: La Guette peatland
Road ditch
• Originally, the vegetation is mainly Sphagnum mosses…
• Source of C in 2013 and 2014 (D’Angelo et al.)
• The site is characterised by 2 hydrological sub-systems

## Slide 5
• Hydrological restoration in the downstream sub-system (upstream as a control):
To raise the water table depth and promote the soil rewetting
To reduce water table fluctuations
• Set up of of trenches dug in the peat soil and filled with sand and bentonite
• conversion of the straight ditch into meanders to slow down water flow
10m
Restoration works_______________________________________________________
D926 ROAD
THE PEATLAND
outlet
THE DITCH

## Slide 6
2 m
• Set up of 2 experimental stations (in Downstream and Upstream)
Sphagnum experiments__________________________________________
Experimental Stations
One of the two experimental Stations
6
• In each station, 3 treatments: (i) control (intact plots), (ii) bare peat (removal of vegetation and first 5 cm of peat), and (iii) Sphagnum treatment (bare peat with Sphagnum capitula spread on the surface)
• Each treatment in 4 replicates
Experiments started in February 2014

## Slide 7
In each station (12 plots), we measured monthly at the pick biomass:
- CO2 and CH4 fluxes with a closed static chamber (Vaisala probe for CO2 and a portable IR laser absorption spectrometer for CH4);
- Plant species abundance => a 50-50 cm gridded frame placed above a marked subplot.
- Water table level and water chemistry: monitored in the whole site.
Hydro
CO2, CH4
Végétation
The monitored environmental variables_______________________________
Vegetation
2m
2m

## Slide 8
C
Control
Bare peat by striping
B
In July 2016
Striping + Sphagnum
S
In April 2016
Sphagnum experiments__________________________________________
After 2 years…
Sphagnum mosses
Eriophorum angustifolium

## Slide 9
Sphagnum plot #1
Control plot #1
Sphagnum plot #2
Control plot #2
Within Care-Peat project, upscaling of previous Sphagnum experiments
Fine scale experimental stations
Automatic piezometer
• The restoration works made in 2 parts of the pilot to take into account the variation of the WTD, a key factor to the successful development of Sphagnum species
• Surface: total of 4 plots of 600 m2 each – 2 control plots (total of 1200 m2) paired to 2 Sphagnum plots (total of 1200 m2)

## Slide 10
Upscaling of previous Sphagnum experiments within Care-Peat project
• ACTIVITY I2.1 / Procedures to prepare the restoration works February 2019 to March 2020
DI2.1.1: Report of the preliminary site visit : ISTO together with the site manager (CCVF) and the Dpt Council (CD18) visited the site and decided of the exact areas of the experiment => March 2019
D12.1.2: Map drawing of the experimental plots => April 2019
February 2019 to June 2021
Coordinator: CNRS – ISTO, FR
DI2.1.3: Jointly refined restoration plan => Sept 2019?
DI2.1.4: Reports of the administrative procedures necessary to get permissions for the works (Regional Biodiversity agency, Regional Science Council Natural Heritage, the DREAL) => Oct 2019
DI2.1.5: Tendering procedures and final choice of the contractors (describe the work and post an offer in the market to select the company) => Dec 2019
DI2.1.6.: Report of the collection of Sphagnum => March 2020

## Slide 11
• ACTIVITY I2.2 / Realisation of the pilot March 2020 to April 2020
DI2.2.1: Report of the spreading of Sphagnum: ~0.25 kg of fresh Sphagnum green parts per m2 will be spread over the plot. A control zone will be associated to each plot => April 2020
DI2.2.2: Reports on walkboard construction to avoid trampling of the soil => April 2020
• ACTIVITY I2.3 / Activation of the transfer knowledge April 2020 to June 2021
DI2.3.1: Writing a technical note => allowing replication to other sites => June 2021

## Slide 12
Thank you!

## Slide 13
Ecosystem Respiration
Gross Primary Production
Net Ecosystem Exchange
CH4
24
CH4
10
Peatland
- 301
GPP
ER
DOC
1240
8
957
Peatland
- 138
GPP
ER
DOC
1281
16
1184
2013
2014
gC m-2 yr-1
SOURCE functioning
Monitoring for 2 years of CO2, CH4 and DOC… 20 plots randomly distributed in the peatland
C budget = source functioning______________________________________________

## Slide 14
20
10
0
Q mean (L s-1
2009
2010
2011
2012
2013
2014
=> Frequent lowering / high fluctuations of groundwater table level
Hydrological disturbances__________________________________________
(month average)
WTD (cm)
=> Rise of water flow at the peatland outlet